## Slide 1
FY2027 CALL FOR PROPOSALS
Research Proposal
Standard submission template · complete this deck to present to the Steering Committee. It follows the same structure as the Word version.
PROJECT TITLE
Enter your project title
LEAD RESEARCHER & INSTITUTION
Name, title, institution
PRIORITY SCOPE ADDRESSED
Name the scope from Section 2 of the call
FOCUS AREA — keep yours, delete the rest
Integrated Mining & Processing
Mining stream / Coal Processing stream
Surface Environment
Future Technologies
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 1

## Slide 2
How to use this template
Guidance the italic guidance on each slide tells you what to write. Replace it with your content, and delete anything in grey brackets before you submit.
Work slide by slide
Every section of the required structure is one slide. Keep the order; the reviewers score against it.
Cost it inside the template
The budget slides carry the Coaltech rate card
Stage-gate every milestone
Each milestone needs the test Coaltech will apply to accept and pay it, plus measurable success criteria.
Show the plan as a Gantt
The work plan slide takes a Gantt chart. Align it to your milestones.
Submit as one PDF
Maximum 20 pages, font 11pt or larger, to cbergman@coaltech.co.za, subject line “Coaltech FY2027 Proposal, [focus area]”.
Before you submit
One PDF, 20 pages or fewer, 11 pt or larger
Focus area and priority scope named on the cover
All sections complete; guidance text deleted
Budget ex VAT, VAT shown separately, rate card applied
Every milestone has a stage gate and success criteria
Work plan shown as a Gantt chart
Team demographics complete; letters of support attached
Co-funding disclosed in full, or stated as none
Technology transfer mechanism described
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 2

## Slide 3
How your proposal is scored
Impact and implementation carry the highest weighting.
45%
Impact & implementation
A real operational problem addressed, and results the sector can use, with a route to pilot where the work allows. Building on existing work counts.
25%
Alignment
A clear fit with a named focus area and priority scope, and relevance to the sector.
15%
Innovation & value for money
Originality, technical soundness, and a budget matched to the work and the rate card.
15%
Team & resources
A qualified team, access to facilities, and student development.
Co-funding counts in a proposal’s favour where it exists. It is not a requirement, and proposals without it are assessed on the same basis.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 3

## Slide 4
Proposal details
Guidance complete every field. This is the cover information reviewers see first.
Project title
Enter your project title
Lead researcher
Name, title, institution
Co-researchers
Names, titles, institutions
Institution / organisation
Primary institution and address
Focus area & stream
IMP (Mining / Coal Processing stream) / Surface Environment / Future Technologies
Priority scope addressed
From Section 2 of the call, e.g. discard and ultra-fines to product
Cross-cutting enabler (if any)
Digitalisation and technology / Alternative uses of coal
Project duration
Months, with start and end dates from Apr 2027
Total budget requested
R ex VAT; VAT shown separately in Section 10
Co-funding
Source, amount and share, or “none at this stage”
Contact
Email and phone
Institutional sign-off
Name and role of authorising officer
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 4

## Slide 5
1
Executive summary
Guidance half a page in plain language: the problem, the work, and the expected benefit to the sector. Write it once the rest is settled.
1.1 Project overview
The problem and its significance · your objectives and research questions · your approach · fit with the focus area and priority scope.
1.2 Expected outcomes
Scientific and industry outcomes · value created for the sector · student development · technology transfer potential.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 5

## Slide 6
2
Research problem
Guidance describe the gap in current knowledge or practice, and the priority scope from the call that your work responds to. Be specific.
2.1 Problem statement
Current state of knowledge and the gap · the specific challenge or opportunity · significance for the coal industry · the research questions you will answer.
2.2 Alignment
Integrated Mining & Processing
Surface Environment
Future Technologies
Keep your focus area above, delete the others. State the priority scope, and why this matters to the sector now.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 6

## Slide 7
3
Industry impact & implementation
Guidance this section carries 45% of the evaluation. Describe the value the work creates and how its results will be used in practice.
45%
3.1 Sector importance & value creation
Pick one or two and justify: value creation · operational improvement · environmental benefit · social impact. Turning a liability (discard, ultra-fines, brine) into a product is strongly favoured.
3.2 Implementation pathway
Current technology readiness level and pathway · how findings transfer to industry · industry partner, if any · timeline to real-world impact.
Research
→
Validate
→
Pilot
→
Demonstrate
→
Adopt
If your work sits on this pathway, indicate where it ends. Some research does not lead to a pilot; where that is the case, state the intended use of the results instead.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 7

## Slide 8
4
Methodology
Guidance set out the method, what is new in it, and how the results will be validated.
4.1 Research design
Experimental or field framework · controlled variables · data collection methods · analysis and interpretation.
4.2 Technical innovation
What is novel · equipment and technologies · validation, quality assurance and testing protocols.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 8

## Slide 9
5
Approach
Guidance set out the phases of the work and how the project will be managed from day to day.
1
Phase 1
[Name the phase, its dates, and the one outcome it must produce]
2
Phase 2
[Name the phase, its dates, and the one outcome it must produce]
3
Phase 3
[Name the phase, its dates, and the one outcome it must produce]
5.2 Execution plan
Team roles and reporting · stakeholder engagement · quality assurance · how you adapt if a line of work fails.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 9

## Slide 10
6
Work plan & timeline
Guidance a Gantt chart is mandatory. Show phases, activities, dependencies and the critical path, aligned to your milestones.
Paste your Gantt chart here
Start no earlier than 1 April 2027 · phases with start and end dates · dependencies and critical path · milestones from Section 7 marked on the bars
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 10

## Slide 11
7
Deliverables, milestones & stage gates
Guidance SMART deliverables only. The stage gate is the test Coaltech applies before the milestone is accepted and paid.
# | Target date | Deliverable | Stage gate (acceptance test) | Success criteria
M1 | [MM/YYYY] | [What will be delivered — be specific] | [How Coaltech confirms it is genuinely done] | [Measurable criteria]
M2 | [MM/YYYY] | [What will be delivered — be specific] | [How Coaltech confirms it is genuinely done] | [Measurable criteria]
M3 | [MM/YYYY] | [What will be delivered — be specific] | [How Coaltech confirms it is genuinely done] | [Measurable criteria]
M4 | [MM/YYYY] | [What will be delivered — be specific] | [How Coaltech confirms it is genuinely done] | [Measurable criteria]
Final | [MM/YYYY] | [Final report and project outcomes] | [How Coaltech confirms it is genuinely done] | [Measurable criteria]
Technology transfer mechanism: [state how the technology or knowledge moves to the sector — a guideline, a demonstration, a licence, a member trial]
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 11

## Slide 12
8
Risk management
Guidance list the main risks, their impact and probability, and the mitigation for each.
Risk | Impact | Probability | Level | Mitigation
[Risk 1] | [H/M/L] | [H/M/L] | [H/M/L] | [How you manage it]
[Risk 2] | [H/M/L] | [H/M/L] | [H/M/L] | [How you manage it]
[Risk 3] | [H/M/L] | [H/M/L] | [H/M/L] | [How you manage it]
[Risk 4] | [H/M/L] | [H/M/L] | [H/M/L] | [How you manage it]
Risk matrix
Med
High
High
Low
Med
High
Low
Low
Med
Impact →
Probability ↑
Any risk rated High needs a named owner and a point at which it is escalated to Coaltech.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 12

## Slide 13
9
Team & resources
Guidance the research team, their roles and expertise, and the institutional support behind them. Student development is encouraged and forms part of the evaluation.
Role | Name & expertise | Citizenship | Demographics
Lead researcher | [Name, qualifications, role] | [SA / Foreign] | [BF / BM / WF / WM]
Co-researcher 1 | [Name, qualifications, role] | [SA / Foreign] | [BF / BM / WF / WM]
Co-researcher 2 | [Name, qualifications, role] | [SA / Foreign] | [BF / BM / WF / WM]
Student(s) | [Name, qualifications, role] | [SA / Foreign] | [BF / BM / WF / WM]
BF black female · BM black male · WF white female · WM white male
9.2 Institutional support
Facilities and equipment · technical and administrative support · industry partnerships · letters of support attached.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 13

## Slide 14
10a
Budget by category
Guidance all amounts ex VAT, VAT at 15% shown separately. Year 1 runs April 2027 to March 2028. Rates above the card by 10% or more need motivation.
Category (ex VAT) | Year 1 (R) | Year 2 (R) | Total (R)
Personnel (incl. bursary) | [ ] | [ ] | [ ]
Equipment | [ ] | [ ] | [ ]
Materials | [ ] | [ ] | [ ]
Travel | [ ] | [ ] | [ ]
Analysis / other | [ ] | [ ] | [ ]
Subtotal (ex VAT) | [ ] | [ ] | [ ]
VAT (15%) | [ ] | [ ] | [ ]
TOTAL (incl VAT) | [ ] | [ ] | [ ]
COALTECH RATE CARD · 2026/27 MAXIMA, EX VAT
PhD stipend
162,000 pa
MSc stipend
134,000 pa
Postdoctoral fellow
340,000 pa
Professor / PI (billed)
80,000 pa
Senior researcher
153,000 pa
L1 director / partner
9,100 /day
L3 senior consultant
3,800 /day
L5 junior professional
1,200 /day
University overhead
up to 15%
Subcontractors
max 40%
Full tables and later years: CT-GUIDE-2026-001 v1.1
Budget justification: [personnel and student development · equipment · materials · travel · co-funding · value for money]
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 14

## Slide 15
10b
Budget per milestone & co-funding
Guidance tie the money to Section 7. Coaltech pays on delivery and acceptance.
# | Deliverable | Start | End | Budget ex VAT | Incl VAT
M1 | [Deliverable] | [MM/YY] | [MM/YY] | R [ ] | R [ ]
M2 | [Deliverable] | [MM/YY] | [MM/YY] | R [ ] | R [ ]
M3 | [Deliverable] | [MM/YY] | [MM/YY] | R [ ] | R [ ]
M4 | [Deliverable] | [MM/YY] | [MM/YY] | R [ ] | R [ ]
Final | [Deliverable] | [MM/YY] | [MM/YY] | R [ ] | R [ ]
TOTAL |  |  |  | R [ ] | R [ ]
Co-funding
Source | Amount (R) | Share
Coaltech | [ ] | [ ]%
[Co-funder name] | [ ] | [ ]%
Co-funding is welcomed but not required; a proposal without it is assessed on the same basis. Disclose all sources in full, or state that there are none.
ADVANCING THE FUTURE OF SUSTAINABLE COAL
FY2027 Proposal Template · 15